## Risk Register
TAVARES CLAIMS SERVICES, INC. — ENTERPRISE RISK REGISTER
Prepared by Chris Morrissey ¦ Review cycle: Quarterly ¦ Fictional organization. Created for portfolio demonstration purposes.
Risk ID | Date Identified | Risk Category | Risk Description | Asset / Process Affected | Threat Source | Vulnerability | Inherent Likelihood (1-5) | Inherent Impact (1-5) | Inherent Risk Score | Inherent Risk Level | Existing Controls | Control Effectiveness (1-5) | Residual Likelihood (1-5) | Residual Impact (1-5) | Residual Risk Score | Residual Risk Level | Risk Treatment | Treatment Plan / Next Actions | Risk Owner | Target Remediation Date | Status
R-001 | 2026-01-08 | Data Protection | Unencrypted PHI backups stored in legacy on-prem NAS accessible to broader IT staff than required | Patient claims data warehouse | External attacker / Malicious insider | Backup volumes not encrypted at rest; excessive access group membership | 4 | 5 |  |  | Encrypted nightly backups migrated to AWS S3 with SSE-KMS; access restricted to 3-person backup admin group | 4 | 2 | 2 |  |  | Mitigate | Complete migration to encrypted cloud backup by Q2; decommission legacy NAS; run access recertification | VP Infrastructure | 2026-05-18 | In Progress
R-002 | 2026-01-08 | Access Control | Shared service account used by three ETL pipelines with standing admin privileges to production database | Production PHI database | Insider threat / Credential compromise | No individual accountability; standing privileged access; password not rotated | 4 | 5 |  |  | Service account rotated quarterly; database activity logging enabled | 3 | 3 | 2 |  |  | Mitigate | Migrate ETL to IAM role-based auth (no static creds); implement just-in-time privileged access via PAM tool | Director of Engineering | 2026-04-24 | In Progress
R-003 | 2026-01-13 | Third-Party / Vendor | Claims clearinghouse vendor (ClaimLink Corp) has not provided a current SOC 2 Type II report | Eligibility verification workflow | Vendor breach / Supply chain compromise | No independent assurance of vendor control environment in past 18 months | 3 | 4 |  |  | Vendor contract includes data protection addendum; annual security questionnaire on file | 2 | 3 | 3 |  |  | Mitigate | Escalate to procurement; request updated SOC 2 Type II or bridge letter; evaluate alternate vendor if unresolved by contract renewal | Vendor Risk Manager | 2026-03-25 | Open
R-004 | 2026-01-20 | Business Continuity | Single AWS region deployment with no tested failover for claims processing platform | Claims processing application (us-east-1) | Regional outage / Natural disaster | No multi-region redundancy; DR runbook untested in 14 months | 3 | 5 |  |  | Daily automated snapshots; documented (but untested) DR runbook | 3 | 4 | 3 |  |  | Mitigate | Stand up warm standby in us-west-2; conduct tabletop DR exercise; update BIA recovery time objectives | Director of Infrastructure | 2026-06-24 | Open
R-005 | 2026-01-22 | Application Security | Customer-facing patient portal has not undergone penetration testing since acquisition of PortalWorks platform | Patient self-service portal | External attacker | Unknown vulnerability posture on acquired codebase | 4 | 4 |  |  | WAF in front of portal; automated SAST scanning in CI pipeline | 3 | 3 | 3 |  |  | Mitigate | Commission third-party penetration test; remediate critical/high findings before next release | AppSec Lead | 2026-03-19 | Open
R-006 | 2026-02-02 | Insider Threat | Departed employees' access not consistently deprovisioned within policy SLA (24 hours) | All SaaS applications (Okta-federated) | Malicious/negligent former employee | Manual offboarding checklist; no automated SSO deprovisioning trigger | 3 | 4 |  |  | HR ticketing triggers manual IT offboarding task; monthly access audit | 3 | 2 | 3 |  |  | Mitigate | Automate deprovisioning via Okta Lifecycle Management tied to HRIS termination event | IAM Manager | 2026-04-13 | In Progress
R-007 | 2026-02-05 | Compliance / Regulatory | Business Associate Agreements (BAAs) not on file for 2 of 11 active subcontractors handling PHI | Vendor management program | Regulatory (HHS OCR) | Contract lifecycle gap; no centralized BAA tracking system | 2 | 5 |  |  | Legal review required before vendor onboarding (policy exists, enforcement inconsistent) | 2 | 2 | 4 |  |  | Mitigate | Build centralized BAA tracker; obtain missing BAAs within 30 days; add BAA checkpoint to procurement workflow | Compliance Officer | 2026-03-10 | Open
R-008 | 2026-02-10 | Cloud / Infrastructure | Production AWS S3 buckets identified with overly permissive bucket policies during quarterly config review | Data lake / analytics staging | External attacker / Data exposure | Misconfiguration; no automated guardrail preventing public ACLs | 3 | 5 |  |  | AWS Config rules deployed post-discovery; buckets remediated same day as found | 1 | 4 | 1 |  |  | Mitigate | Enable AWS Config conformance pack + SCP to block public bucket policies account-wide; add to CI/CD pre-deploy checks | Cloud Security Engineer | 2026-02-25 | In Progress
R-009 | 2026-02-10 | Physical Security | Colocation data center badge access logs not reviewed on a recurring schedule | Legacy colocation facility (non-AWS) | Unauthorized physical access | No formal quarterly physical access review process | 2 | 4 |  |  | Badge system with logging; visitor escort policy | 2 | 2 | 3 |  |  | Accept | Add colo badge log review to quarterly physical security checklist; Medium residual risk (score 6) given facility is being decommissioned in migration plan | Facilities / Security Manager | 2026-05-04 | Open
R-010 | 2026-02-18 | Change Management | Emergency changes to production billing system bypass standard change advisory board (CAB) review | Billing and revenue cycle system | Operational error | Emergency change process lacks retrospective review requirement | 3 | 4 |  |  | Emergency changes logged in ticketing system after the fact | 3 | 2 | 3 |  |  | Mitigate | Require mandatory 48-hour post-implementation CAB review for all emergency changes; track in change management KPIs | IT Change Manager | 2026-04-07 | Open
R-011 | 2026-02-20 | Data Protection | Marketing analytics team exports de-identified patient datasets to local laptops for ad-hoc analysis | Analytics / BI environment | Data loss / Device theft | No DLP controls on endpoint; de-identification method not independently validated | 3 | 3 |  |  | Endpoint encryption (BitLocker/FileVault) enforced via MDM | 3 | 2 | 2 |  |  | Mitigate | Deploy DLP policy restricting bulk export; validate de-identification methodology against Safe Harbor standard; move analysis to governed workspace | Data Governance Lead | 2026-05-27 | Open
R-012 | 2026-02-25 | Third-Party / Vendor | Payment processor integration relies on deprecated TLS 1.1 fallback for backward compatibility with one legacy client | Payment gateway integration | External attacker (protocol downgrade) | Legacy client dependency delaying TLS 1.1 deprecation | 2 | 4 |  |  | TLS 1.2+ enforced for 98% of traffic; monitoring on legacy endpoint | 2 | 2 | 3 |  |  | Mitigate | Migrate final legacy client to TLS 1.2 by contract deadline; disable TLS 1.1 fallback entirely | Director of Engineering | 2026-06-05 | Open
R-013 | 2026-03-02 | Human Resources / Security Awareness | Phishing simulation click rate (14%) exceeds industry benchmark and internal target (5%) | All employees (email) | External attacker (phishing/BEC) | Insufficient security awareness training cadence; no role-based training for high-risk groups | 4 | 3 |  |  | Annual security awareness training; email banner tagging for external senders | 3 | 2 | 2 |  |  | Mitigate | Move to quarterly phishing simulations; targeted training for finance and HR (BEC-high-risk); track click rate as security KPI | Security Awareness Lead | 2026-04-24 | In Progress
R-014 | 2026-03-05 | Application Security | API rate limiting not enforced on provider directory public API, enabling potential scraping/enumeration | Provider directory API (public) | External attacker (data scraping) | No rate limiting or bot detection at API gateway | 3 | 2 |  |  | API gateway logging enabled; basic authentication required for write operations | 2 | 2 | 1 |  |  | Accept | Accepted under ACC-014 by Elena Voss, COO, on 2026-03-12. Public directory data and Low residual score 2 do not justify immediate remediation cost. Monitor abuse; retain Q3 rate-limiting backlog. See Risk Acceptance for authority and conditions. | API Platform Lead | 2026-07-24 | Open
R-015 | 2026-03-10 | Business Continuity | Key-person dependency: single engineer holds undocumented knowledge of legacy claims adjudication rules engine | Claims adjudication system | Operational / Staffing | No documentation; no cross-training; high attrition risk role | 3 | 4 |  |  | None formal; tribal knowledge only | 3 | 4 | 3 |  |  | Mitigate | Document rules engine logic and decision tables; cross-train second engineer; add to succession plan. Inherent score 12 ties R-003, R-006, R-010, R-013 and R-017; R-015 stays at 12 residual because no formal controls are recorded. | Engineering Manager | 2026-05-18 | Open
R-016 | 2026-03-17 | Third-Party / Vendor | ClaimLink Corp contract allows 5 business days to notify Tavares of a confirmed breach, and ClaimLink last tested its IR plan 14 months ago | Breach notification process (HIPAA Breach Notification Rule) | Vendor breach / Delayed notification | Notification window negotiated before Tavares set an internal 72-hour vendor standard; contract auto-renewed 2026-01-13 on existing terms | 2 | 4 |  |  | BAA executed with ClaimLink; annual security questionnaire (V-001) on file | 2 | 2 | 3 |  |  | Mitigate | Amend BAA to require notice within 72 hours of discovery; request ClaimLink IR tabletop results with the SOC 2 Type II delivery tracked under R-003 | Vendor Risk Manager | 2026-07-13 | Open
R-017 | 2026-03-19 | Third-Party / Vendor | Offsite paper-records vendor DataVault Records Mgmt (V-006) holds archived PHI, scored 65 at its last assessment, and has no SOC 2 report on file | Archived paper PHI records (storage and destruction) | Vendor breach / Improper disposal | Calculated vendor rating is High, but the sign-off and remediation plan required for High-rated vendors were never recorded | 3 | 4 |  |  | Vendor inventory flags High rating; annual questionnaire on file | 2 | 3 | 3 |  |  | Mitigate | Obtain Vendor Risk Manager and Compliance Officer sign-off with a remediation plan before the 2026-04-07 renewal, or move archived records to a vendor that can evidence certified destruction | Compliance Officer | 2026-04-07 | Open

## Legend & Methodology
RISK REGISTER — METHODOLOGY & LEGEND
Risk Scoring | Risk Score = Likelihood (1-5) x Impact (1-5). Range 1-25.
Critical | 15-25 — Immediate executive escalation and remediation required
High | 10-14 — Remediation plan required within 30-60 days
Medium | 5-9 — Remediation plan required within 90 days, or documented risk acceptance
Low | 1-4 — Monitor; remediate opportunistically or formally accept
Likelihood Scale | 1=Rare, 2=Unlikely, 3=Possible, 4=Likely, 5=Almost Certain
Impact Scale | 1=Negligible, 2=Minor, 3=Moderate, 4=Major, 5=Severe (regulatory, financial, or patient-safety consequence)
Risk Treatment Options | Accept = retain risk within tolerance; Mitigate = reduce likelihood/impact via controls; Transfer = insurance/contract; Avoid = discontinue the activity
How to use this cells | Blue-bordered numeric cells (Likelihood/Impact/Effectiveness) are the editable inputs. Risk Score and Risk Level columns are formulas — do not hardcode.
Review Cadence | Full register reviewed quarterly by the GRC function; Critical/High risks reviewed monthly by risk owners; register updated continuously as new risks are identified.

## Risk Acceptance
TAVARES RISK ACCEPTANCE RECORD
Scenario status | Fictional decision and personnel, authored for this portfolio exercise. No real executive approval is represented.
Acceptance ID | ACC-014
Related risk | R-014
Decision | Accept with monitoring
Accepter | Elena Voss
Role | Chief Operating Officer
Delegated authority | Scenario risk charter delegates acceptance of Low residual operational risks involving public data to the COO. No authority to waive legal obligations or accept PHI disclosure risk.
Decision date | 2026-03-12
Residual score at decision | 2
Residual band | Low
Business rationale | The directory is public by design. Immediate rate-limiting work would displace higher-priority PHI and access-control remediation; expected scraping exposure does not justify that cost. Q3 implementation remains in the backlog.
Risk owner | API Platform Lead
Conditions | Review gateway abuse logs monthly; escalate service degradation, unexpected nonpublic data exposure, or a material change in API usage to the COO and CISO. Acceptance must be reconsidered if any condition fails.
Scheduled review date | 2026-07-24
Acceptance expires | 2026-12-31
Review evidence | This record documents the March decision only. A completed July review or renewal is not supplied.
Closure evidence | Rate-limiting configuration and validation of expected API behavior are required to close the remediation action. Acceptance alone does not close R-014.