## Dashboard
Pinecastle - SOC 2 Readiness and Evidence
Controls |  | Readiness Area | Ready | Partial | Not Ready | Main Issue
Ready Controls |  | Access Control |  |  |  | MFA exceptions and review evidence
Partial Controls |  | Security Operations |  |  |  | IR tabletop and vulnerability evidence
Not Ready Controls |  | Availability |  |  |  | Restore evidence
Open Findings |  | Vendor / Cloud |  |  |  | Critical vendor and cloud exception review
Readiness |  | Governance / Evidence |  |  |  | Evidence ownership and policy cadence
Assessment Date | 2026-09-11
TOTAL

## Control Matrix
Control ID | Control Name | TSC Area | Trust Service Category | Owner | Frequency | Readiness Status | Evidence Needed | Evidence Review Priority | Readiness Area
AC-01 | MFA Enforcement | CC6 | Security | VP of IT | Continuous | Partial | MFA configuration and enrollment report | High | Access Control
AC-02 | Access Reviews | CC6 | Security | GRC Lead | Quarterly | Partial | Q access review evidence | Medium | Access Control
AC-03 | Terminated User Removal | CC6 | Security | People Ops | Per termination | Ready | Termination ticket and deactivation log | Medium | Access Control
VM-01 | Vulnerability Scanning | CC7 | Security | Security Engineer | Monthly | Partial | Monthly scan report | Medium | Security Operations
VM-02 | Critical Vulnerability SLA | CC7 | Security | Security Engineer | Monthly | Partial | Aging report and exceptions | Medium | Security Operations
LOG-01 | Security Logging | CC7 | Security | Security Ops | Continuous | Partial | Log source inventory | Medium | Security Operations
IR-01 | Incident Response Plan | CC7 | Security | CISO | Annual | Ready | Approved IR plan | Medium | Security Operations
IR-02 | Incident Tabletop | CC7 | Security | CISO | Annual | Not Ready | Tabletop evidence | Medium | Security Operations
BC-01 | Backup Monitoring | A1 | Availability | Infrastructure | Daily | Ready | Backup logs | Medium | Availability
BC-02 | Restore Testing | A1 | Availability | Infrastructure | Annual | Partial | Restore test record | Medium | Availability
TPRM-01 | Critical Vendor Review | CC9 | Security | GRC Lead | Annual | Partial | Vendor review evidence | High | Vendor / Cloud
CHG-01 | Production Change Approval | CC8 | Security | Engineering | Per change | Ready | Pull request approvals | Medium | Security Operations
SEC-01 | Security Awareness Training | CC2 | Security | People Ops | Annual | Partial | Training completion report | Low | Governance / Evidence
POL-01 | Security Policy Review | CC1 | Security | GRC Lead | Annual | Partial | Approved policies | Medium | Governance / Evidence
DATA-01 | Data Retention | C1 | Confidentiality | Legal | Annual | Partial | Retention matrix | Medium | Governance / Evidence
CLD-01 | Cloud Configuration Monitoring | CC7 | Security | Cloud Engineering | Monthly | Partial | Configuration report | High | Vendor / Cloud
HR-01 | Background Checks | CC1 | Security | People Ops | Per hire | Ready | Background screening evidence | Low | Governance / Evidence
PRIV-01 | Privacy Commitments | P1 | Privacy | Legal | Annual | Partial | Privacy notice and DPA | Medium | Governance / Evidence
EVD-01 | Evidence Ownership | CC3 | Security | GRC Lead | Monthly | Partial | Evidence owner matrix | Medium | Governance / Evidence
RISK-01 | Risk Register Review | CC3 | Security | CISO | Quarterly | Ready | Risk register review record | Medium | Governance / Evidence
TRUST-01 | Customer Assurance Responses | CC2 | Security | GRC Lead | As needed | Partial | Questionnaire response archive | Low | Governance / Evidence
MON-01 | Security Metrics Reporting | CC4 | Security | CISO | Quarterly | Partial | Security metrics dashboard | Medium | Governance / Evidence

## PBC Tracker
Request ID | Control ID | Evidence Requested | Owner | Due Date | Status | Auditor-Style Comment | Priority
PBC-001 | AC-01 | MFA configuration export | VP of IT | 2026-09-16 | Received | Covers employees; contractor exceptions need follow-up | High
PBC-002 | AC-02 | Q2 access review evidence | GRC Lead | 2026-09-23 | Partial | Missing approval timestamp | Medium
PBC-003 | VM-01 | Monthly vulnerability scan reports | Security Engineer | 2026-09-25 | Received | Need aging summary | Medium
PBC-004 | IR-02 | Incident tabletop evidence | CISO | 2026-10-20 | Missing | No current-year exercise | Medium
PBC-005 | BC-02 | Backup restoration test | Infrastructure | 2026-10-27 | Partial | Restore test scheduled | Medium
PBC-006 | TPRM-01 | Critical vendor review evidence | GRC Lead | 2026-09-25 | Partial | DataFlow findings open | High
PBC-007 | CHG-01 | Production change sample | Engineering | 2026-09-25 | Received | No exception noted | Medium
PBC-008 | SEC-01 | Training completion report | People Ops | 2026-10-05 | Partial | Contractor report missing | Low
PBC-009 | POL-01 | Approved policy set | GRC Lead | 2026-09-16 | Received | Review calendar needed | Medium
PBC-010 | CLD-01 | Cloud configuration monitoring report | Cloud Engineering | 2026-10-16 | Partial | Exceptions not formally reviewed | High
PBC-011 | LOG-01 | Log source inventory and alert routing matrix | Security Ops | 2026-10-05 | Missing | Inventory not started; see SOCF-006 | Medium
PBC-012 | EVD-01 | Evidence owner matrix | GRC Lead | 2026-09-25 | Partial | Draft names owners for 14 of 22 controls | Medium
PBC-013 | PRIV-01 | Privacy notice and customer DPA template | Legal | 2026-10-09 | Received | DPA subprocessor list predates DataFlow AI | Low

## Audit Findings
Finding ID | Control ID | Finding | Severity | Root Cause | Corrective Action | Owner | Target Date | Status
SOCF-001 | AC-01 | Contractor MFA evidence incomplete | High | Contractor identity process outside normal evidence review | Require contractor MFA report and update onboarding | VP of IT | 2026-09-25 | Open
SOCF-002 | AC-02 | Access review approval evidence incomplete | Medium | Manual review evidence lacks timestamp | Adopt dated approval workflow | GRC Lead | 2026-10-20 | Open
SOCF-003 | IR-02 | No current-year tabletop evidence | Medium | Exercise not completed before readiness review | Conduct tabletop and retain lessons learned | CISO | 2026-11-12 | Planned
SOCF-004 | VM-02 | Critical vulnerability SLA exceptions not formally approved | Medium | Exception process not consistently documented | Require risk acceptance for overdue criticals | Security Engineer | 2026-10-27 | Open
SOCF-005 | EVD-01 | Evidence ownership decentralized | Medium | Evidence retained across multiple team folders | Create evidence owner matrix and central tracker | GRC Lead | 2026-09-25 | In Progress
SOCF-006 | LOG-01 | No log source inventory or named alert owners for SaaS audit logs | Medium | Logging was enabled tool by tool with no inventory step | Build log source inventory and alert routing matrix | Security Ops | 2026-10-27 | Open

## Remediation Tracker
Finding ID | Action | Owner | Target Date | Status | Validation Method | Executive Escalation | Closure Evidence
SOCF-001 | Require contractor MFA report and update onboarding | VP of IT | 2026-09-25 | Open | Inspect updated evidence and confirm exception closure | Escalate if not closed before audit period | Contractor MFA report showing every active contractor enrolled
SOCF-002 | Adopt dated approval workflow | GRC Lead | 2026-10-20 | Open | Inspect updated evidence and confirm exception closure | Track in readiness sprint | Next quarterly review with a dated approval
SOCF-003 | Conduct tabletop and retain lessons learned | CISO | 2026-11-12 | Planned | Inspect updated evidence and confirm exception closure | Track in readiness sprint | Exercise report and lessons-learned tickets
SOCF-004 | Require risk acceptance for overdue criticals | Security Engineer | 2026-10-27 | Open | Inspect updated evidence and confirm exception closure | Track in readiness sprint | Approved exception record for each overdue critical
SOCF-005 | Create evidence owner matrix and central tracker | GRC Lead | 2026-09-25 | In Progress | Inspect updated evidence and confirm exception closure | Track in readiness sprint | Evidence owner matrix covering all 22 controls
SOCF-006 | Build log source inventory and alert routing matrix | Security Ops | 2026-10-27 | Open | Inspect inventory against cloud, identity, and SaaS sources; test one alert route end to end | Track in readiness sprint | Inventory plus one tested alert route per critical source

## Readiness Report
Readiness Summary
Overall Status | Partially Ready | Executive Message | Do not begin audit period until high-priority evidence gaps close.
Top Blocker | Contractor MFA evidence | Severity | High
60-90 Day Sprint | Close access, IR, vulnerability, backup, and evidence ownership gaps. | Owner | CISO / GRC
Report Type | Type I first. The Type II observation window starts only after the readiness retest passes. | Decision Owner | CISO
Next Step | Complete remediation tracker and conduct internal readiness retest. | Target | 2026-11-25
Customer Value | Improves security questionnaire responses and future audit readiness. | Customer Commitment | No audit date promised to customers until the retest passes
Audit Risk | Missing or incomplete evidence may delay audit or create exceptions. | Decision | Readiness sprint required
Assessment Date | 2026-09-11 | Primary Criteria | AICPA Trust Services Criteria

## References
Reference | URL | Use
NIST CSF 2.0 | https://www.nist.gov/cyberframework | Program outcomes and governance alignment
NIST SP 800-53 Rev. 5 Release 5.2.0 | https://csrc.nist.gov/News/2025/nist-releases-revision-to-sp-800-53-controls | Control catalog reference
NIST SP 800-53A Rev. 5 | https://csrc.nist.gov/pubs/sp/800/53/a/r5/final | Control assessment and test procedure reference
CIS Controls v8.1 | https://www.cisecurity.org/controls/v8-1 | Practical safeguard mapping
ISO/IEC 27001:2022/Amd 1:2024 | https://www.iso.org/standard/88435.html | ISMS requirements
ISO/IEC 27002:2022 | https://www.iso.org/standard/75652.html | Security control guidance
ISO/IEC 27017:2026 | https://www.iso.org/standard/43757.html | Cloud-service control guidance
AICPA Trust Services Criteria with revised points of focus 2022 | https://www.aicpa-cima.com/resources/download/2017-trust-services-criteria-with-revised-points-of-focus-2022 | SOC 2 readiness criteria
NIST SP 800-61 Rev. 3 | https://csrc.nist.gov/pubs/sp/800/61/r3/final | Incident-response control guidance
NIST SP 800-161 Rev. 1 Update 1 | https://csrc.nist.gov/pubs/sp/800/161/r1/upd1/final | Supply-chain controls
Scenario dates and rating definitions | Fictional assessment assumptions; see shared company profile | ../../00-company-profile/Pinecastle-Company-and-GRC-Scope.md