## POA&M
TAILSPIN CIVIC SYSTEMS, INC. — PLAN OF ACTION AND MILESTONES (POA&M) | [17 empty] | Status Date (input): | 2026-03-31
AwardWorks Platform (SaaS) ¦ FedRAMP Moderate ¦ Reporting Period: Q1 2026 ¦ Status Date: 2026-03-31 ¦ Fictional organization. Created for portfolio demonstration purposes.
POA&M ID | Weakness Name | Weakness Description | Source of Discovery | NIST 800-53 Control(s) | Asset Identifier | Severity | Likelihood | Impact | Risk Rating | Point of Contact | Remediation Plan | Scheduled Completion Date | Milestones | Status | Days Open | Overdue? | Deviation / Risk Acceptance
V-001 | Untimely Remediation of High-Severity Vulnerabilities | Authenticated vulnerability scans identified 14 High-severity findings that exceeded the FedRAMP 30-day remediation window for Moderate systems. Root cause: patching pipeline lacked automated escalation when an SLA breach was approaching. | Monthly ConMon Scan / 3PAO Assessment | RA-5, SI-2 | Application Tier (web-app-prod-01 through 06) | High | High | High | High | Director of Platform Engineering | Implement automated SLA-based escalation in the vulnerability management pipeline; remediate the 14 open High findings; institute weekly SLA burn-down review. | 2026-06-30 | M1: Remediate all open High findings (2026-05-15); M2: Deploy automated SLA escalation (2026-06-15); M3: Validate with clean scan cycle (2026-06-30) | In Progress
V-002 | Configuration Drift from Approved Hardening Baseline | Assessment sampling identified three application servers with configuration settings deviating from the approved CIS Level 1 hardening baseline, including a non-compliant SSH configuration and a disabled host-based audit daemon. | 3PAO Assessment (Technical Test) | CM-6 | app-srv-04, app-srv-07, app-srv-11 | Moderate | Moderate | Moderate | Moderate | Cloud Infrastructure Lead | Re-image affected hosts from the approved AMI; enable AWS Config drift detection with automatic remediation for baseline settings; add drift check to deployment gate. | 2026-05-31 | M1: Re-image affected hosts (2026-04-15); M2: Enable Config auto-remediation rules (2026-05-15); M3: Add pre-deploy drift gate to CI (2026-05-31) | In Progress
V-003 | Incomplete Logging of Privileged Function Use | Privileged function execution on the legacy reporting subsystem is not forwarded to the centralized SIEM, creating a gap in the audit trail for administrative actions on that component. | 3PAO Assessment (Technical Test) | AC-6(9), AU-2 | reporting-svc-legacy | Moderate | Moderate | High | Moderate | Security Operations Lead | Deploy log forwarding agent to the legacy reporting subsystem; validate privileged-action event coverage against the approved auditable events list; confirm SIEM ingestion and alerting. | 2026-05-15 | M1: Deploy forwarding agent (2026-04-20); M2: Validate event coverage (2026-05-05); M3: Confirm SIEM alerting rules fire (2026-05-15) | In Progress
V-004 | Annual System Recovery Exercise Not Performed | Full-system recovery and reconstitution procedures have not been exercised within the required annual period. Component-level backup restoration has been tested, but an end-to-end recovery validating documented RTO/RPO has not been conducted. | 3PAO Assessment (Interview/Examine) | CP-10 | AwardWorks Platform (system-wide) | Moderate | Low | High | Moderate | Director of Infrastructure | Conduct a full-system recovery exercise in an isolated environment; measure actual RTO/RPO against documented objectives; update the Contingency Plan based on exercise findings. | 2026-07-31 | M1: Develop exercise scenario and success criteria (2026-05-30); M2: Execute recovery exercise (2026-07-15); M3: Update Contingency Plan and after-action report (2026-07-31) | Open
V-005 | Inconsistent Audit Log Review Evidence | The documented weekly audit log review procedure was not consistently evidenced for a two-month period. Reviews may have occurred but were not recorded in a manner that supports assessment. | 3PAO Assessment (Examine) | AU-6 | SIEM Platform | Low | Moderate | Low | Low | Security Operations Lead | Implement a ticketed workflow that generates an auditable record for each weekly log review, including reviewer, date, findings, and escalations; backfill process documentation. | 2026-04-30 | M1: Build ticketed review workflow (2026-04-10); M2: Complete four consecutive evidenced review cycles (2026-04-30) | In Progress
V-006 | Incident Reporting Timeline Not Exercised | The one-hour US-CERT and FedRAMP ISSO incident notification requirement is documented in the Incident Response Plan but has not been validated through a tabletop or live exercise, creating uncertainty about the organization's ability to meet the timeline. | 3PAO Assessment (Interview) | IR-6, IR-4 | Incident Response Program | Moderate | Moderate | Moderate | Moderate | Incident Response Lead | Conduct a tabletop exercise specifically testing notification timelines to US-CERT and the FedRAMP ISSO; document actual elapsed times; update the IR Plan and contact roster based on results. | 2026-06-15 | M1: Develop tabletop scenario (2026-05-01); M2: Execute tabletop with Legal and Communications (2026-06-01); M3: Update IR Plan and roster (2026-06-15) Later evidence (AAR approved 2026-06-04, sections 8–11): original 2026-06-15 completion is incompatible with corrective actions due 2026-06-30 and 2026-07-15. Reason: notification draft took 64 minutes against 60; severity classification was delayed. Follow-up exercise recommended by 2026-09-30. Original date retained; approved revised closure date not recorded. | Open
V-007 | Late Submission of Continuous Monitoring Deliverables | Monthly continuous monitoring deliverables (scan results, POA&M updates, inventory) were submitted after the required deadline in two of the last six reporting cycles. | FedRAMP ConMon Review | CA-7 | ConMon Program | Low | Moderate | Low | Low | ISSO | Automate ConMon deliverable assembly and add calendar-driven internal deadlines five business days ahead of the external due date; assign a documented backup submitter. | 2026-05-31 | M1: Automate deliverable package generation (2026-05-01); M2: Establish internal deadline and backup owner (2026-05-15); M3: Two consecutive on-time cycles (2026-05-31) | In Progress
V-008 | Shared Service Account Used by Batch Processing Jobs | A shared service account with elevated database privileges is used by four batch processing jobs, preventing attribution of database actions to a specific process and violating least-privilege and individual-accountability requirements. | Internal Self-Assessment | AC-2, AC-6 | awardworks-batch-db | Moderate | High | Moderate | High | Director of Platform Engineering | Migrate each batch job to a dedicated IAM database role scoped to the minimum required privileges; eliminate the shared account; verify attribution in database audit logs. | 2026-08-31 | M1: Inventory required privileges per job (2026-05-30); M2: Create scoped roles and migrate jobs (2026-07-31); M3: Disable shared account and validate logs (2026-08-31) | Open

## POA&M Summary
POA&M SUMMARY — Q1 2026
Counts derived from the POA&M tab.
Risk Rating | Open | In Progress | Closed | Total
High
Moderate
Low
TOTAL
Overdue Items
Next Milestone Due

## Legend
POA&M — LEGEND & METHODOLOGY
Purpose | The Plan of Action and Milestones is the authoritative tracking document for every security weakness identified in a federal system. It is a required deliverable under FISMA and FedRAMP and is submitted to the Authorizing Official on a monthly continuous monitoring cadence.
Editable input cell | Cell U1 on the POA&M tab (yellow) is the Status Date. Change it and the Overdue? column recalculates against every scheduled completion date.
Sources of Discovery | 3PAO Assessment ¦ Monthly ConMon Scan ¦ Internal Self-Assessment ¦ Penetration Test ¦ Incident ¦ FedRAMP ConMon Review ¦ Customer-Reported
Risk Rating | Derived from Likelihood and Impact. FedRAMP remediation timelines: High = 30 days, Moderate = 90 days, Low = 180 days from discovery.
Traceability | Each POA&M ID maps back to a control marked 'Other Than Satisfied' in the SCTM, and forward to the findings documented in the Security Assessment Report.
Deviation / Risk Acceptance | Where a weakness cannot be remediated within required timelines, a formal deviation request (Risk Adjustment, False Positive, or Operational Requirement) must be submitted to and approved by the Authorizing Official.
Closure | A POA&M item may only be closed with evidence of remediation validated by the ISSO — typically a clean scan, a re-test result, or an assessed artifact.