## Dashboard
Northbridge - NIST CSF 2.0 Gap Assessment
Assessed Outcomes |  |  | CSF Function | Outcomes | High Priority | Main Theme | Near-Term Focus
Implemented |  |  | GOVERN |  |  | Accountability, risk appetite, vendor oversight | Quarterly risk review
Partially Implemented |  |  | IDENTIFY |  |  | Assets, vulnerabilities, improvement tracking | Inventory and SLA governance
Not Implemented |  |  | PROTECT |  |  | Access, training, configuration, data protection | Privileged MFA and baselines
High Priority Gaps |  |  | DETECT |  |  | Logging, alert ownership, triage | Log and alert ownership
Assessment Date | 2026-08-19 |  | RESPOND |  |  | IR plan, communications, tabletop | Tabletop exercise
|  |  | RECOVER |  |  | Backup restoration, DR, customer communications | Restore testing
Highest Priority Gaps | Function | Status | Risk | Recommendation | Owner | Priority | Roadmap
GV.OC-01 | GOVERN | Partially Implemented | Medium | Create annual security strategy review tied to business goals | CISO | High | 0-30 days
GV.RM-01 | GOVERN | Partially Implemented | High | Define risk appetite and escalation thresholds | CISO / CFO | High | 31-90 days
GV.RR-02 | GOVERN | Partially Implemented | Medium | Create control-owner matrix | GRC Lead | High | 31-90 days
GV.SC-04 | GOVERN | Partially Implemented | High | Implement vendor tiering and annual critical vendor assessment | Procurement / GRC | High | 31-90 days
ID.AM-01 | IDENTIFY | Partially Implemented | High | Assign owners and reconcile assets monthly | IT Operations | High | 31-90 days

## CSF Assessment
CSF ID | Function | Outcome | Current Status | Current Evidence | Target State | Gap | Business Risk | Recommendation | Owner | Priority | Roadmap Phase | Framework References
GV.OC-01 | GOVERN | Organizational context and mission understood | Partially Implemented | Company profile exists; customer obligations known | Documented business context, security objectives, and customer commitments reviewed annually | Security objectives not formally reviewed with leadership | Medium | Create annual security strategy review tied to business goals | CISO | High | 0-30 days | NIST SP 1308; ISO 27001 Clause 4
GV.RM-01 | GOVERN | Risk management objectives established | Partially Implemented | Risk register created in Project 1 | Approved cyber risk appetite/tolerance and escalation criteria | Risk appetite not formally approved | High | Define risk appetite and escalation thresholds | CISO / CFO | High | 31-90 days | NIST IR 8286 Rev. 1
GV.RR-02 | GOVERN | Cybersecurity roles and responsibilities assigned | Partially Implemented | Owners listed in risk register | Named control owners and backup owners for key domains | Ownership not complete for every key control | Medium | Create control-owner matrix | GRC Lead | High | 31-90 days | ISO 27001 Clause 5
GV.PO-01 | GOVERN | Cybersecurity policies established | Partially Implemented | Policy set exists | Policies approved, reviewed annually, and mapped to controls | Policy review cadence inconsistent | Medium | Approve annual policy review calendar | GRC Lead | Medium | 0-30 days | ISO 27001 Clause 5; SOC 2 CC1
GV.SC-04 | GOVERN | Supplier risk managed | Partially Implemented | Vendor list exists | Risk-tiered vendor program with annual critical vendor reviews | Critical vendor tiering incomplete | High | Implement vendor tiering and annual critical vendor assessment | Procurement / GRC | High | 31-90 days | NIST SP 800-161 Rev. 1 Update 1; CIS 15
ID.AM-01 | IDENTIFY | Assets inventoried | Partially Implemented | Cloud and SaaS systems known | Authoritative asset inventory with owner and criticality | Inventory not consistently owned or reconciled | High | Assign owners and reconcile assets monthly | IT Operations | High | 31-90 days | CIS 1, CIS 2
ID.RA-01 | IDENTIFY | Vulnerabilities identified and documented | Partially Implemented | Scanning occurs | Vulnerability findings tracked to SLA with exception workflow | SLA evidence inconsistent | High | Adopt remediation SLA and exception process | Security Engineer | High | 31-90 days | NIST 800-53 RA-5; CIS 7
ID.IM-02 | IDENTIFY | Improvements identified from assessments | Partially Implemented | Project risk assessment and CSF assessment exist | Assessment findings tracked through closure | No standing governance cadence for findings | Medium | Create monthly remediation review | GRC Lead | Medium | 31-90 days | NIST IR 8286C Rev. 1
PR.AA-01 | PROTECT | Identities and credentials managed | Partially Implemented | SSO and MFA enabled | Centralized identity lifecycle with enforced MFA and reviewed exceptions | Privileged MFA exceptions and reviews need improvement | High | Enforce phishing-resistant MFA for admins and quarterly access reviews | VP of IT | High | 0-30 days | NIST 800-53 IA-2; CIS 6
PR.AT-01 | PROTECT | Personnel receive security awareness | Partially Implemented | Annual training exists | Training completion evidenced for employees and contractors | Contractor training evidence incomplete | Medium | Expand training tracker to contractors | People Operations | Medium | 31-90 days | NIST 800-53 AT-2; CIS 14
PR.DS-01 | PROTECT | Data-at-rest protected | Implemented | Cloud encryption standards enabled | Encryption enforced and reviewed for data stores | No material gap identified for baseline encryption | Low | Continue periodic configuration review | Cloud Engineering | Low | 6-12 months | ISO 27002; ISO 27017:2026
PR.PS-01 | PROTECT | Configuration management practiced | Partially Implemented | IaC and change reviews exist | Configuration baselines monitored with security exceptions tracked | Cloud configuration monitoring incomplete | High | Implement configuration monitoring and monthly owner review | Cloud Engineering | High | 31-90 days | NIST 800-53 CM-2; CIS 4
DE.CM-01 | DETECT | Networks and services monitored | Partially Implemented | Cloud and SaaS logs available | Critical logs mapped, retained, alerted, and owned | Alert ownership and coverage not fully mapped | High | Map critical log sources and alert owners | Security Operations | High | 31-90 days | NIST 800-53 SI-4; CIS 8
DE.AE-02 | DETECT | Potentially adverse events analyzed | Partially Implemented | Some alerts reviewed | Alert triage procedure with documented escalation | Triage documentation inconsistent | Medium | Document alert triage and escalation criteria | Security Operations | Medium | 3-6 months | NIST SP 800-61 Rev. 3
RS.MA-01 | RESPOND | Incident response executed | Partially Implemented | IR plan exists | Plan tested through tabletop with lessons learned | No recent tabletop exercise | High | Conduct tabletop exercise and track corrective actions | CISO | High | 3-6 months | NIST SP 800-61 Rev. 3; CIS 17
RS.CO-03 | RESPOND | Information shared with stakeholders | Partially Implemented | Escalation contacts exist | Legal, customer, executive communications playbook tested | Communication playbook not exercised | High | Add stakeholder communications to tabletop | Legal / CISO | High | 3-6 months | NIST SP 800-61 Rev. 3
RC.RP-01 | RECOVER | Recovery plan executed | Partially Implemented | Backups exist | Recovery tested against RTO/RPO | Recovery testing evidence incomplete | High | Perform backup restoration and DR test | Infrastructure | High | 3-6 months | NIST 800-53 CP-10; CIS 11
RC.CO-03 | RECOVER | Recovery activities communicated | Not Implemented | No formal evidence | Recovery communications plan for customers and executives | No tested recovery communications plan | Medium | Create recovery communications template and exercise it | Customer Operations / Legal | Medium | 6-12 months | NIST CSF 2.0 Recover

## Roadmap
Roadmap Phase | Action | Related CSF IDs | Owner | Priority | Expected Evidence | Success Measure | Interview Talking Point
0-30 days | Approve security governance owners and policy review calendar | GV.OC-01, GV.PO-01 | CISO / GRC | High | Approved calendar, owner matrix | Owners assigned for key controls | Governance turns framework results into accountability
0-30 days | Remove unmanaged privileged MFA exceptions | PR.AA-01 | VP of IT | High | MFA policy export, exception log | 100% admin MFA enforcement or approved exception | Existing MFA is not enough if privileged exceptions are unmanaged
31-90 days | Implement vendor risk tiering and critical vendor reviews | GV.SC-04 | Procurement / GRC | High | Vendor inventory, tiering matrix, review evidence | Critical vendors identified and review cadence set | Supply-chain risk is part of cybersecurity governance
31-90 days | Adopt vulnerability remediation SLA and reporting | ID.RA-01 | Security Engineer | High | SLA policy, vulnerability aging report | Overdue critical vulnerabilities reported monthly | A scanner is only useful if findings are governed
31-90 days | Map critical log sources and alert owners | DE.CM-01 | Security Operations | High | Log source inventory, alert routing matrix | Critical alerts have named owner | Detection maturity depends on coverage and ownership
3-6 months | Conduct incident-response tabletop | RS.MA-01, RS.CO-03 | CISO / Legal | High | Exercise agenda, participant list, lessons learned | Corrective actions opened and tracked | Plans must be exercised to prove readiness
3-6 months | Perform backup restoration and DR test | RC.RP-01 | Infrastructure | High | Restore test record, RTO/RPO results | Recovery objective met or gap documented | Recovery is not proven until tested
6-12 months | Build SOC 2 readiness evidence inventory | GV.RR-02, ID.IM-02 | GRC Lead | Medium | Evidence tracker, owner assignments | Evidence owners and review cadence established | CSF gap work feeds audit readiness

## References
Reference | URL | Use in Workbook
NIST CSF 2.0 | https://www.nist.gov/cyberframework | Primary program framework and functions
NIST SP 800-30 Rev. 1 | https://csrc.nist.gov/pubs/sp/800/30/r1/final | Risk-assessment methodology
NIST IR 8286 Rev. 1 | https://csrc.nist.gov/pubs/ir/8286/r1/final | Cybersecurity risk integration with ERM
NIST IR 8286A Rev. 1 | https://csrc.nist.gov/pubs/ir/8286/a/r1/final | Risk identification and estimation for ERM
NIST IR 8286C Rev. 1 | https://csrc.nist.gov/pubs/ir/8286/c/r1/final | Risk staging and governance oversight
NIST SP 1308 | https://csrc.nist.gov/pubs/sp/1308/final | CSF 2.0, ERM, and workforce management
NIST SP 800-53 Rev. 5 Release 5.2.0 | https://csrc.nist.gov/News/2025/nist-releases-revision-to-sp-800-53-controls | Control catalog reference
NIST SP 800-53A Rev. 5 | https://csrc.nist.gov/pubs/sp/800/53/a/r5/final | Control assessment reference
NIST SP 800-161 Rev. 1 Update 1 | https://csrc.nist.gov/pubs/sp/800/161/r1/upd1/final | Supply-chain risk reference
CIS Controls v8.1 | https://www.cisecurity.org/controls/v8-1 | Prioritized safeguards
ISO/IEC 27001:2022/Amd 1:2024 | https://www.iso.org/standard/88435.html | ISMS requirements
ISO/IEC 27002:2022 | https://www.iso.org/standard/75652.html | Security control guidance
AICPA TSC revised points of focus 2022 | https://www.aicpa-cima.com/resources/download/2017-trust-services-criteria-with-revised-points-of-focus-2022 | SOC 2 criteria reference
NIST SP 800-61 Rev. 3 | https://csrc.nist.gov/pubs/sp/800/61/r3/final | Incident response
NIST SP 800-171 Rev. 3 | https://csrc.nist.gov/pubs/sp/800/171/r3/final | CUI reference where relevant
ISO/IEC 27017:2026 | https://www.iso.org/standard/43757.html | Cloud-specific control guidance
PCI DSS v4.0.1 | https://www.pcisecuritystandards.org/document_library/ | Payment-card reference where relevant
Scenario dates and rating definitions | Fictional assessment assumptions; see shared company profile | ../../00-company-profile/Northbridge-Company-and-GRC-Scope.md