## Dashboard
Northbridge - Third-Party Risk Assessment
Vendor | DataFlow AI |  | Domain | Weight | Score | Weighted | Highest Risk
Risk Tier | Critical
Assessment Decision | Conditional Approval
Weighted Score
High Findings
Open Findings
Assessment Date | 2026-08-13
Top Findings | Domain | Severity | Risk | Recommendation | Owner | Due Date | Status
F-001 | IAM | High | Unauthorized administrative access could affect customer data and service integrity. | Require privileged MFA evidence before production integration. | DataFlow AI Security Lead | 2026-09-30 | Open
F-002 | Legal / Incident Response | High | Northbridge may not receive timely notice needed for customer and legal obligations. | Add contract language for timely notification and required incident details. | Northbridge Legal | 2026-09-20 | Open
F-003 | Application Security | Medium | Application weaknesses may remain undiscovered longer than Northbridge's target risk tolerance. | Require annual penetration test or documented compensating control. | DataFlow AI Security Lead | 2026-10-31 | In Progress
F-004 | Incident Response | Medium | Response roles and communications may be untested during a customer-impacting incident. | Request tabletop evidence or scheduled exercise date. | DataFlow AI Compliance Manager | 2026-11-15 | Open
F-005 | Security Awareness | Low | Contractors may not receive the same security awareness expectations as employees. | Expand training evidence to contractor population. | DataFlow AI HR / Compliance | 2026-12-15 | Planned

## Vendor Profile
Vendor Profile and Inherent Risk
Vendor | DataFlow AI | Service | AI-assisted customer-support analytics
Data Types | Confidential customer business data; support metadata; limited user identifiers | Hosting | Cloud SaaS
Integration | API integration with Northbridge application and Salesforce | Business Owner | Customer Operations
Inherent Risk Tier | Critical | Assessment Type | Pre-contract security review
Risk Rationale | Processes customer data and integrates with production support workflow | Decision | Conditional Approval
Review Frequency | Annual critical vendor review | Next Review | 2027-08-13
Primary Framework | NIST SP 800-161 Rev. 1 Update 1 | Supporting Frameworks | NIST CSF 2.0, CIS v8.1, ISO, SOC 2
Data Location | United States cloud region assumed | Subprocessors | Disclosed by vendor
Contract Status | Security exhibit under legal review | Risk Acceptance Required | No, if high findings close before production
Assessment Owner | Northbridge GRC Lead | Assessment Date | 2026-08-13

## Questionnaire
Domain | Question | Response | Evidence Reviewed | Score | Framework Reference
Governance | Does the vendor maintain an information security program with assigned ownership? | Yes | Security policy and org chart | 4 | ISO 27001 Clause 5; NIST CSF GV.RR
Governance | Are security policies reviewed at least annually? | Partial | Policy set provided, review cadence unclear | 3 | ISO 27001 Clause 5; SOC 2 CC1
IAM | Is MFA required for workforce access? | Yes | MFA policy | 4 | CIS 6; NIST 800-53 IA-2
IAM | Is MFA required and evidenced for privileged administrators? | Partial | Policy provided, admin evidence missing | 2 | CIS 6; NIST 800-53 IA-2
IAM | Are access reviews performed for privileged users? | Partial | Access review summary, no sample evidence | 3 | NIST 800-53 AC-2; SOC 2 CC6
Data Security | Is customer data encrypted at rest and in transit? | Yes | Architecture and encryption statement | 5 | ISO 27002; ISO 27017
Data Security | Are retention and deletion requirements documented? | Yes | Retention policy | 4 | ISO 27002; SOC 2 Confidentiality
Data Security | Are subprocessors disclosed? | Yes | Subprocessor list | 4 | NIST CSF GV.SC
Infrastructure | Are vulnerability scans performed regularly? | Yes | Vulnerability procedure | 4 | CIS 7; NIST 800-53 RA-5
Infrastructure | Are critical vulnerabilities remediated under SLA? | Partial | SLA exists, aging evidence limited | 3 | CIS 7; NIST 800-53 SI-2
Infrastructure | Are cloud configuration controls monitored? | Partial | Cloud control summary | 3 | ISO 27017; CIS 4
Application Security | Does the vendor maintain secure SDLC practices? | Yes | SDLC policy | 4 | CIS 16; NIST 800-53 SA-10
Application Security | Is independent penetration testing performed annually? | No | Last test summary shows two-year cadence | 2 | SOC 2 CC7; CIS 18
Application Security | Are high and critical findings tracked to closure? | Partial | Summary remediation statement | 3 | NIST 800-53 CA-5
Incident Response | Does the vendor maintain an incident-response plan? | Yes | IR plan | 4 | NIST SP 800-61 Rev. 3
Incident Response | Has the incident-response plan been tested recently? | No | Unable to test — evidence not provided. No tabletop evidence (F-004). | 2 | NIST SP 800-61 Rev. 3; CIS 17
Incident Response | Are breach notification obligations contractually defined? | Partial | Contract language lacks timeline | 2 | SOC 2 CC7; Legal requirement
Business Continuity | Does the vendor maintain BCP/DR procedures? | Yes | BCP statement | 4 | NIST 800-53 CP family
Business Continuity | Are recovery objectives documented and tested? | Partial | RTO/RPO provided, test evidence limited | 3 | NIST 800-53 CP-4, CP-10
Compliance | Is a SOC 2 or equivalent assurance report available? | Yes | SOC 2 executive summary | 4 | AICPA TSC
Compliance | Are audit exceptions tracked and remediated? | Partial | Exception summary provided | 3 | SOC 2 CC4; CC5
Privacy | Does the vendor document data processing and privacy obligations? | Yes | DPA and privacy summary | 4 | ISO 27001; SOC 2 Privacy
Contract | Are security requirements included in the contract? | Partial | Security exhibit provided | 3 | NIST CSF GV.SC
Contract | Are right-to-audit or assurance-review rights included? | Partial | Annual assurance review allowed | 3 | NIST SP 800-161
Monitoring | Will Northbridge receive security status or risk updates? | Partial | Customer portal available, no formal cadence | 3 | NIST CSF GV.SC

## Scorecard
Domain | Weight | Score | Weighted Score | Assessment Notes | Highest Risk
Governance | 10% | 4 |  | Policies and security ownership exist; risk-review cadence needs improvement. | Medium
IAM | 20% | 3 |  | MFA exists, but privileged MFA evidence is incomplete. | High
Data Security | 20% | 4 |  | Encryption, retention, and deletion practices are documented. | Medium
Infrastructure Security | 15% | 4 |  | Cloud controls exist; configuration evidence is limited. | Medium
Application Security | 15% | 3 |  | Secure SDLC exists; penetration testing cadence is below target. | Medium
Incident Response and BCP | 10% | 3 |  | Plans exist, but tabletop and notification evidence are incomplete. | High
Compliance and Assurance | 10% | 4 |  | SOC 2 evidence is available; exceptions require follow-up. | Medium
Overall Weighted Score
Decision Threshold | >=80% Approve; 65%-79% Conditional; <65% Reject | Decision

## Findings Register
Finding ID | Domain | Finding | Severity | Evidence Reviewed | Risk | Recommendation | Owner | Due Date | Status | Validation Evidence
F-001 | IAM | Privileged MFA evidence incomplete | High | Vendor provided MFA policy but not an administrator enrollment export or exception list. | Unauthorized administrative access could affect customer data and service integrity. | Require privileged MFA evidence before production integration. | DataFlow AI Security Lead | 2026-09-30 | Open | MFA configuration export, admin enrollment evidence, approved exception log
F-002 | Legal / Incident Response | Breach notification terms not contractually specific | High | Security exhibit references incident notification but does not define timeline or minimum content. | Northbridge may not receive timely notice needed for customer and legal obligations. | Add contract language for timely notification and required incident details. | Northbridge Legal | 2026-09-20 | Open | Executed contract addendum or redlined clause
F-003 | Application Security | Penetration testing occurs every two years | Medium | Vendor provided last external test summary from 2025 and stated testing is every two years. | Application weaknesses may remain undiscovered longer than Northbridge's target risk tolerance. | Require annual penetration test or documented compensating control. | DataFlow AI Security Lead | 2026-10-31 | In Progress | Updated testing schedule or compensating-control approval
F-004 | Incident Response | Tabletop exercise evidence not provided | Medium | Unable to test — evidence not provided. Vendor provided incident-response plan but no recent exercise report. | Response roles and communications may be untested during a customer-impacting incident. | Request tabletop evidence or scheduled exercise date. | DataFlow AI Compliance Manager | 2026-11-15 | Open | Exercise report, participant list, lessons learned
F-005 | Security Awareness | Contractor training evidence incomplete | Low | Training report covered employees but did not show contractor completion. | Contractors may not receive the same security awareness expectations as employees. | Expand training evidence to contractor population. | DataFlow AI HR / Compliance | 2026-12-15 | Planned | Training completion report including contractors

## Remediation Tracker
Finding ID | Required Action | Owner | Due Date | Status | Days Until Due | Escalation | Closure Criteria
F-001 | Require privileged MFA evidence before production integration. | DataFlow AI Security Lead | 2026-09-30 | Open |  | Escalate to CISO if overdue | MFA configuration export, admin enrollment evidence, approved exception log
F-002 | Add contract language for timely notification and required incident details. | Northbridge Legal | 2026-09-20 | Open |  | Escalate to CISO if overdue | Executed contract addendum or redlined clause
F-003 | Require annual penetration test or documented compensating control. | DataFlow AI Security Lead | 2026-10-31 | In Progress |  | Track in vendor review | Updated testing schedule or compensating-control approval
F-004 | Request tabletop evidence or scheduled exercise date. | DataFlow AI Compliance Manager | 2026-11-15 | Open |  | Track in vendor review | Exercise report, participant list, lessons learned
F-005 | Expand training evidence to contractor population. | DataFlow AI HR / Compliance | 2026-12-15 | Planned |  | Track in vendor review | Training completion report including contractors
Formulas:
Days Until Due = DATEDIF(DATE(2026,8,13),[Due Date],"d")

## Decision Memo
Vendor Decision Memo
Vendor | DataFlow AI | Decision | Conditional Approval
Business Need | AI-assisted support analytics for customer operations | Risk Tier | Critical
Rationale | Vendor has a reasonable security foundation, but high findings must close before full production use. | Score
Required Conditions | Privileged MFA evidence; breach-notification language; annual penetration test commitment; IR tabletop evidence. | Approval Owner | CISO / Legal / Customer Operations
Production Use | Limited implementation only until high findings are closed. | Risk Acceptance | Not recommended for unresolved high findings
Executive Message | This is a managed business-risk decision, not a simple pass/fail checklist. | Next Review | 2027-08-13
Interview Talking Point | Conditional approval supports the business while preserving risk accountability. | Assessment Date | 2026-08-13
Portfolio Skill | Vendor classification, evidence review, findings, remediation tracking, and decision documentation. | Primary Standard | NIST SP 800-161 Rev. 1 Update 1

## References
Reference | URL | Use in Workbook
NIST SP 800-161 Rev. 1 Update 1 | https://csrc.nist.gov/pubs/sp/800/161/r1/upd1/final | Supply-chain cybersecurity risk methodology
NIST CSF 2.0 | https://www.nist.gov/cyberframework | Governance and supply-chain outcome alignment
NIST IR 8286 Rev. 1 | https://csrc.nist.gov/pubs/ir/8286/r1/final | Enterprise-risk reporting context
NIST SP 800-53 Rev. 5 Release 5.2.0 | https://csrc.nist.gov/News/2025/nist-releases-revision-to-sp-800-53-controls | Control references
NIST SP 800-53A Rev. 5 | https://csrc.nist.gov/pubs/sp/800/53/a/r5/final | Evidence and assessment logic
NIST SP 800-61 Rev. 3 | https://csrc.nist.gov/pubs/sp/800/61/r3/final | Incident response and notification review
CIS Controls v8.1 | https://www.cisecurity.org/controls/v8-1 | Practical safeguard mapping
ISO/IEC 27001:2022/Amd 1:2024 | https://www.iso.org/standard/88435.html | ISMS alignment
ISO/IEC 27002:2022 | https://www.iso.org/standard/75652.html | Security control guidance
ISO/IEC 27017:2026 | https://www.iso.org/standard/43757.html | Cloud-service control considerations
AICPA TSC revised points of focus 2022 | https://www.aicpa-cima.com/resources/download/2017-trust-services-criteria-with-revised-points-of-focus-2022 | SOC 2 evidence review