## Dashboard
Northbridge - Cyber Risk Assessment
Total Risks | 20 |  | Residual Rating | Count | Management Meaning | Primary Action | Escalation
Critical Residual Risks | 0 |  | Critical | 0 | Immediate leadership decision | Escalate and fund | Executive
High Residual Risks | 14 |  | High | 14 | Prioritized remediation | Track to due date | CISO / owner
Open / Planned Actions | 20 |  | Medium | 6 | Managed through plan | Monitor | Control owner
Top Residual Score | 15 |  | Low | 0 | Routine monitoring | Maintain | Operational
Assessment Date | 2026-08-13
Top Residual Risks | Business Process | Asset | Residual Score | Residual Rating | Treatment | Owner | Due Date
R-001 | Identity and Access Management | Okta / Microsoft 365 / AWS Admin | 15 | High | Mitigate | VP of IT | 2026-10-15
R-002 | Business Continuity | Production SaaS Platform | 15 | High | Mitigate | Director of Infrastructure | 2026-11-30
R-003 | Cloud Security | AWS S3 / IAM / Network Configurations | 15 | High | Mitigate | Cloud Engineering Manager | 2026-10-31
R-007 | Third-Party Risk | Customer Data Processors | 15 | High | Mitigate | GRC Lead | 2026-12-31
R-015 | Incident Response | Enterprise Incident Process | 15 | High | Mitigate | CISO | 2026-11-15

## Methodology
Risk Scoring Methodology
Likelihood | Label | Definition | Impact | Label | Definition
1 | Rare | Not expected, but possible under unusual circumstances | 1 | Minimal | Limited internal inconvenience
2 | Unlikely | Could occur, but not expected annually | 2 | Minor | Some operational disruption or limited data exposure
3 | Possible | Could occur within the next year | 3 | Moderate | Material process disruption, customer impact, or audit finding
4 | Likely | Expected or observed in comparable SaaS environments | 4 | Major | Significant customer, legal, financial, or operational impact
5 | Almost Certain | Expected repeatedly or already occurring | 5 | Severe | Major breach, prolonged outage, regulatory exposure, or board-level impact
Score Range | Rating | Management Meaning
1-4 | Low | Monitor through normal operations
5-9 | Medium | Track with named owner
10-16 | High | Prioritize remediation and report to leadership
17-25 | Critical | Immediate leadership decision required

## Risk Register
Risk ID | Business Process | Asset | Threat | Vulnerability | Risk Statement | Inherent Likelihood | Inherent Impact | Inherent Score | Inherent Rating | Existing Controls | Control Effectiveness | Residual Likelihood | Residual Impact | Residual Score | Residual Rating | Treatment | Action Plan | Risk Owner | Due Date | Status | CSF Function | NIST 800-53 Ref | CIS / Other Ref
R-001 | Identity and Access Management | Okta / Microsoft 365 / AWS Admin | Credential theft | Privileged MFA not consistently phishing-resistant | Unauthorized privileged access may occur because administrator authentication is not consistently hardened, leading to customer data exposure or service disruption. | 5 | 5 | 25 | Critical | MFA, SSO, audit logs | Partially Effective | 3 | 5 | 15 | High | Mitigate | Enforce phishing-resistant MFA for privileged accounts; complete quarterly privileged access review; remove stale admin accounts. | VP of IT | 2026-10-15 | In Progress | GOVERN, PROTECT | AC-2, IA-2 | CIS 6, CIS 5
R-002 | Business Continuity | Production SaaS Platform | Ransomware | Backup restoration not tested end-to-end | Ransomware or destructive malware may disrupt operations because recovery procedures have not been fully validated. | 4 | 5 | 20 | Critical | Endpoint protection, backups, logging | Partially Effective | 3 | 5 | 15 | High | Mitigate | Run backup restore test; confirm RTO/RPO; document executive recovery decision process. | Director of Infrastructure | 2026-11-30 | Planned | RESPOND, RECOVER | CP-9, CP-10, IR-4 | CIS 11, CIS 17
R-003 | Cloud Security | AWS S3 / IAM / Network Configurations | Cloud misconfiguration | Manual configuration review and inconsistent preventive guardrails | Customer data may be exposed because cloud storage, network, or IAM settings could be misconfigured without timely detection. | 4 | 5 | 20 | Critical | AWS IAM, logging, change review | Partially Effective | 3 | 5 | 15 | High | Mitigate | Implement cloud configuration monitoring; require security review for infrastructure changes; review public exposure alerts monthly. | Cloud Engineering Manager | 2026-10-31 | In Progress | IDENTIFY, PROTECT, DETECT | CM-2, AC-3, SI-4 | CIS 4, CIS 12
R-004 | Access Governance | SaaS Applications | Excessive privileges | Access reviews are inconsistent across business applications | Employees may retain excessive privileges because access is not reviewed consistently across SaaS applications. | 4 | 4 | 16 | High | Manager approvals, SSO groups | Partially Effective | 3 | 4 | 12 | High | Mitigate | Define app owners; conduct quarterly access reviews for critical SaaS apps; track exceptions. | GRC Lead | 2026-12-15 | Planned | GOVERN, PROTECT | AC-2, AC-6 | CIS 5, CIS 6
R-005 | Joiner-Mover-Leaver | Okta / SaaS Apps | Former employee access | Offboarding evidence is not centrally retained | Terminated users may retain access because account removal evidence is incomplete across connected SaaS systems. | 3 | 4 | 12 | High | HR ticketing, SSO deactivation | Partially Effective | 2 | 4 | 8 | Medium | Mitigate | Automate deprovisioning checklist; sample monthly terminations; retain evidence. | People Operations Manager | 2026-09-30 | In Progress | PROTECT | AC-2, PS-4 | CIS 5
R-006 | Vendor Management | Critical SaaS Vendors | Vendor outage | Critical vendor continuity requirements not reviewed annually | A critical SaaS vendor outage may disrupt customer support or operations because continuity expectations are not reviewed. | 3 | 4 | 12 | High | Vendor contracts, status pages | Partially Effective | 3 | 3 | 9 | Medium | Transfer / Mitigate | Tier vendors; document continuity requirements; review SOC reports and BCP statements annually. | Procurement Manager | 2027-01-15 | Not Started | GOVERN, IDENTIFY | SR-3, CP-2 | CIS 15
R-007 | Third-Party Risk | Customer Data Processors | Third-party breach | Vendor security reviews are inconsistent by risk tier | Customer data may be exposed through a vendor breach because critical vendors are not assessed with consistent due diligence. | 4 | 5 | 20 | Critical | Contract review, limited questionnaires | Partially Effective | 3 | 5 | 15 | High | Mitigate | Implement NIST SP 800-161-aligned vendor tiering; require annual critical vendor reviews. | GRC Lead | 2026-12-31 | Planned | GOVERN, IDENTIFY | SR-3, SR-6 | CIS 15
R-008 | Data Protection | Backups / Data Stores | Backup failure | Backup monitoring lacks periodic restore evidence | Critical data may not be recoverable because backups are monitored but restoration is not periodically evidenced. | 3 | 5 | 15 | High | Automated backups | Partially Effective | 2 | 5 | 10 | High | Mitigate | Schedule quarterly restore testing and document results. | Director of Infrastructure | 2026-11-30 | Planned | RECOVER | CP-9, CP-10 | CIS 11
R-009 | Vulnerability Management | Production Systems | Known vulnerability exploitation | Remediation SLAs are not consistently enforced | Attackers may exploit known vulnerabilities because critical findings do not always meet remediation SLAs. | 4 | 4 | 16 | High | Scanning, patching | Partially Effective | 3 | 4 | 12 | High | Mitigate | Approve remediation SLA; report overdue critical vulnerabilities; document risk exceptions. | Security Engineer | 2026-10-31 | In Progress | IDENTIFY, PROTECT | RA-5, SI-2 | CIS 7
R-010 | Email Security | Microsoft 365 | Phishing / BEC | User reporting and simulation metrics are immature | Business email compromise may occur because phishing resilience and reporting metrics are not mature. | 4 | 4 | 16 | High | Email filtering, MFA, awareness training | Partially Effective | 3 | 4 | 12 | High | Mitigate | Run quarterly phishing simulation; track reporting rate; tune mailbox protections. | Security Awareness Owner | 2026-12-01 | Planned | PROTECT, DETECT | AT-2, SI-4 | CIS 14, CIS 9
R-011 | Secure SDLC | GitHub Repositories | Source-code exposure | Repository access and secret scanning exceptions not centrally reviewed | Source code or secrets may be exposed because repository access and secret scanning exceptions are not consistently reviewed. | 3 | 5 | 15 | High | GitHub access controls, branch protection | Partially Effective | 2 | 5 | 10 | High | Mitigate | Review repo access quarterly; enforce secret scanning; document exceptions. | Engineering Manager | 2026-11-15 | Planned | PROTECT, DETECT | SA-10, CM-5 | CIS 16
R-012 | Security Monitoring | Cloud and SaaS Logs | Insufficient logging | Log coverage and alert ownership are not formally mapped | Security incidents may go undetected because key logs and alert owners are not fully documented. | 4 | 4 | 16 | High | Cloud logs, SaaS logs, endpoint telemetry | Partially Effective | 3 | 4 | 12 | High | Mitigate | Map critical logs; define alert owners; test alert routing monthly. | Security Operations Lead | 2026-10-31 | In Progress | DETECT | AU-6, SI-4 | CIS 8
R-013 | Patch Management | Endpoints / Servers | Unpatched critical vulnerability | Patch compliance evidence is incomplete | Critical vulnerabilities may remain exploitable because patch compliance is not consistently evidenced. | 4 | 4 | 16 | High | Endpoint management, scanning | Partially Effective | 3 | 4 | 12 | High | Mitigate | Create monthly patch compliance report and exception workflow. | IT Operations Manager | 2026-10-15 | In Progress | PROTECT | SI-2 | CIS 7
R-014 | Vendor Governance | New Vendors | Weak due diligence | No formal inherent-risk questionnaire before onboarding | High-risk vendors may be onboarded without appropriate review because inherent risk is not assessed before contracting. | 3 | 4 | 12 | High | Procurement review | Partially Effective | 3 | 3 | 9 | Medium | Mitigate | Add vendor inherent-risk intake; route high-risk vendors to security review. | Procurement Manager | 2026-09-30 | Planned | GOVERN | SR-3 | CIS 15
R-015 | Incident Response | Enterprise Incident Process | Untested response plan | No recent tabletop exercise | Incident response may be delayed or inconsistent because roles, escalation paths, and communications have not been exercised. | 4 | 5 | 20 | Critical | IR plan, on-call rotation | Partially Effective | 3 | 5 | 15 | High | Mitigate | Run tabletop aligned to NIST SP 800-61 Rev. 3; capture lessons learned and corrective actions. | CISO | 2026-11-15 | Planned | RESPOND | IR-3, IR-4 | CIS 17
R-016 | Data Governance | Customer Data | Excessive retention | Retention rules are not consistently mapped to systems | Customer data may be retained longer than required because retention rules are not mapped and tested across systems. | 3 | 4 | 12 | High | Contract terms, manual deletion | Partially Effective | 2 | 4 | 8 | Medium | Mitigate | Create data retention matrix; sample deletion evidence; align with privacy commitments. | Legal / Privacy Owner | 2027-01-31 | Not Started | GOVERN, IDENTIFY | PT-2, SI-12 | CIS 3
R-017 | Disaster Recovery | Production Platform | Failed DR | DR exercise not performed in last 12 months | Northbridge may fail to restore service within customer expectations because disaster recovery has not been exercised. | 3 | 5 | 15 | High | Backups, infrastructure-as-code | Partially Effective | 3 | 4 | 12 | High | Mitigate | Conduct DR exercise; document RTO/RPO achievement and gaps. | Director of Infrastructure | 2027-02-28 | Not Started | RECOVER | CP-4, CP-10 | CIS 11
R-018 | Change Management | Production Changes | Unauthorized production change | Emergency changes lack consistent post-implementation review | Production instability or security exposure may occur because emergency changes are not consistently reviewed after implementation. | 3 | 4 | 12 | High | Pull requests, approvals | Partially Effective | 2 | 4 | 8 | Medium | Mitigate | Require emergency change review within five business days; sample monthly. | Engineering Manager | 2026-12-15 | Planned | PROTECT | CM-3 | CIS 4
R-019 | Security Training | Workforce | Human error | Training completion evidence is incomplete for contractors | Security incidents may result from human error because awareness training coverage is not fully evidenced for contractors. | 3 | 3 | 9 | Medium | Annual training | Partially Effective | 2 | 3 | 6 | Medium | Mitigate | Extend training tracker to contractors; report overdue completion monthly. | People Operations Manager | 2026-10-31 | In Progress | PROTECT | AT-2 | CIS 14
R-020 | Audit Readiness | Security Evidence | Missing evidence | Control evidence is decentralized | Customer assurance or future SOC 2 readiness may be delayed because control evidence is not centrally organized. | 4 | 4 | 16 | High | Shared folders, ticketing | Partially Effective | 3 | 4 | 12 | High | Mitigate | Create evidence inventory; assign evidence owners; establish monthly evidence review for key controls. | GRC Lead | 2026-12-31 | Planned | GOVERN | CA-2, CA-7 | SOC 2 CC2, CC3, CC5

## Treatment Plan
Risk ID | Residual Rating | Action Plan | Owner | Due Date | Status | Priority | Notes
R-001 | High | Enforce phishing-resistant MFA for privileged accounts; complete quarterly privileged access review; remove stale admin accounts. | VP of IT | 2026-10-15 | In Progress | High | Track in monthly GRC remediation review
R-002 | High | Run backup restore test; confirm RTO/RPO; document executive recovery decision process. | Director of Infrastructure | 2026-11-30 | Planned | High | Track in monthly GRC remediation review
R-003 | High | Implement cloud configuration monitoring; require security review for infrastructure changes; review public exposure alerts monthly. | Cloud Engineering Manager | 2026-10-31 | In Progress | High | Track in monthly GRC remediation review
R-004 | High | Define app owners; conduct quarterly access reviews for critical SaaS apps; track exceptions. | GRC Lead | 2026-12-15 | Planned | High | Track in monthly GRC remediation review
R-005 | Medium | Automate deprovisioning checklist; sample monthly terminations; retain evidence. | People Operations Manager | 2026-09-30 | In Progress | Medium | Track in monthly GRC remediation review
R-006 | Medium | Tier vendors; document continuity requirements; review SOC reports and BCP statements annually. | Procurement Manager | 2027-01-15 | Not Started | Medium | Track in monthly GRC remediation review
R-007 | High | Implement NIST SP 800-161-aligned vendor tiering; require annual critical vendor reviews. | GRC Lead | 2026-12-31 | Planned | High | Track in monthly GRC remediation review
R-008 | High | Schedule quarterly restore testing and document results. | Director of Infrastructure | 2026-11-30 | Planned | High | Track in monthly GRC remediation review
R-009 | High | Approve remediation SLA; report overdue critical vulnerabilities; document risk exceptions. | Security Engineer | 2026-10-31 | In Progress | High | Track in monthly GRC remediation review
R-010 | High | Run quarterly phishing simulation; track reporting rate; tune mailbox protections. | Security Awareness Owner | 2026-12-01 | Planned | High | Track in monthly GRC remediation review
R-011 | High | Review repo access quarterly; enforce secret scanning; document exceptions. | Engineering Manager | 2026-11-15 | Planned | High | Track in monthly GRC remediation review
R-012 | High | Map critical logs; define alert owners; test alert routing monthly. | Security Operations Lead | 2026-10-31 | In Progress | High | Track in monthly GRC remediation review
R-013 | High | Create monthly patch compliance report and exception workflow. | IT Operations Manager | 2026-10-15 | In Progress | High | Track in monthly GRC remediation review
R-014 | Medium | Add vendor inherent-risk intake; route high-risk vendors to security review. | Procurement Manager | 2026-09-30 | Planned | Medium | Track in monthly GRC remediation review
R-015 | High | Run tabletop aligned to NIST SP 800-61 Rev. 3; capture lessons learned and corrective actions. | CISO | 2026-11-15 | Planned | High | Track in monthly GRC remediation review
R-016 | Medium | Create data retention matrix; sample deletion evidence; align with privacy commitments. | Legal / Privacy Owner | 2027-01-31 | Not Started | Medium | Track in monthly GRC remediation review
R-017 | High | Conduct DR exercise; document RTO/RPO achievement and gaps. | Director of Infrastructure | 2027-02-28 | Not Started | High | Track in monthly GRC remediation review
R-018 | Medium | Require emergency change review within five business days; sample monthly. | Engineering Manager | 2026-12-15 | Planned | Medium | Track in monthly GRC remediation review
R-019 | Medium | Extend training tracker to contractors; report overdue completion monthly. | People Operations Manager | 2026-10-31 | In Progress | Medium | Track in monthly GRC remediation review
R-020 | High | Create evidence inventory; assign evidence owners; establish monthly evidence review for key controls. | GRC Lead | 2026-12-31 | Planned | High | Track in monthly GRC remediation review

## References
Reference | URL | Use in Workbook
NIST CSF 2.0 | https://www.nist.gov/cyberframework | Primary program framework and functions
NIST SP 800-30 Rev. 1 | https://csrc.nist.gov/pubs/sp/800/30/r1/final | Risk-assessment methodology
NIST IR 8286 Rev. 1 | https://csrc.nist.gov/pubs/ir/8286/r1/final | Cybersecurity risk integration with ERM
NIST IR 8286A Rev. 1 | https://csrc.nist.gov/pubs/ir/8286/a/r1/final | Risk identification and estimation for ERM
NIST IR 8286C Rev. 1 | https://csrc.nist.gov/pubs/ir/8286/c/r1/final | Risk staging and governance oversight
NIST SP 1308 | https://csrc.nist.gov/pubs/sp/1308/final | CSF 2.0, ERM, and workforce management
NIST SP 800-53 Rev. 5 Release 5.2.0 | https://csrc.nist.gov/News/2025/nist-releases-revision-to-sp-800-53-controls | Control catalog reference
NIST SP 800-53A Rev. 5 | https://csrc.nist.gov/pubs/sp/800/53/a/r5/final | Control assessment reference
NIST SP 800-161 Rev. 1 Update 1 | https://csrc.nist.gov/pubs/sp/800/161/r1/upd1/final | Supply-chain risk reference
CIS Controls v8.1 | https://www.cisecurity.org/controls/v8-1 | Prioritized safeguards
ISO/IEC 27001:2022/Amd 1:2024 | https://www.iso.org/standard/88435.html | ISMS requirements
ISO/IEC 27002:2022 | https://www.iso.org/standard/75652.html | Security control guidance
AICPA TSC revised points of focus 2022 | https://www.aicpa-cima.com/resources/download/2017-trust-services-criteria-with-revised-points-of-focus-2022 | SOC 2 criteria reference
NIST SP 800-61 Rev. 3 | https://csrc.nist.gov/pubs/sp/800/61/r3/final | Incident response
NIST SP 800-171 Rev. 3 | https://csrc.nist.gov/pubs/sp/800/171/r3/final | CUI reference where relevant
ISO/IEC 27017:2026 | https://www.iso.org/standard/43757.html | Cloud-specific control guidance
PCI DSS v4.0.1 | https://www.pcisecuritystandards.org/document_library/ | Payment-card reference where relevant